## Sheet1
Project Title: Soil Monitoring System(ARC)
Project Manager: | Olethokuhle Masango
Project start date: | 07/10/2025 | Project end date: | 05/11/2025
Authorisation Date: |  | To be confirmed upon formal stakeholder agreement and executive approval
Business Problem
Farmers at the Agricultural Research Council (ARC) face challenges in monitoring soil health efficiently and accurately. Many of the processes used to assess soil conditions such as moisture, nutrient levels, and pH are still done manually, which makes data collection slow, inconsistent, and prone to human error. Because of this, important farming decisions like irrigation scheduling, fertilizer application, and crop selection are often based on guesswork rather than real data. This results in wasted resources, reduced crop yields, and poor soil management practices. To address these challenges, ARC requires a low-cost, energy-efficient Internet of Things (IoT) solution that can automatically collect, monitor, and transmit soil data in real time. This solution will support farm workers and probably researchers with reliable data that helps improve crop health, optimize resource use, and promote sustainable agricultural practices.
Project objectives: |  |  |  | Benefits: Benefits to potential stakeholders by doing the project .
1.Develop a functional IoT soil monitoring prototype using sensors to measure soil parameters such as moisture, pH, temperature, EC, and nutrient levels (NPK). |  |  |  | 1. Improved crop yield and quality through data-driven fertilizer and irrigation decisions. By continuously monitoring soil conditions such as moisture, pH, and nutrient levels, the system provides farmers with accurate, real-time data that helps them make informed decisions about when and how much fertilizer or water to apply.
2. Develop a front-end application (dashboard) that allows farm managers and researchers to easily access and interpret soil data. The interface will display real-time sensor readings and historical trends using graphs, charts, and color indicators for soil health. |  |  |  | 2. Reduced operational costs by minimizing unnecessary soil testing and fertilizer use. Traditional soil testing methods involve sending samples to laboratories, which can be time-consuming and expensive, especially for small-scale farmers. The IoT-based soil monitoring system replaces these manual tests with automated and continuous measurements, drastically reducing the need for frequent lab testing.
3. Ensure data integration and storage through collaboration with the data management team’s database. The soil monitoring system will be integrated with the data management team’s existing database. Collaboration will ensure that all soil readings are securely stored, properly formatted, and can be analyzed. |  |  |  | 3. Real-time soil monitoring that helps detect issues early, reducing risks of crop failure. Continuous soil monitoring allows for early detection of potential problems, such as nutrient deficiencies, pH imbalance, or overly dry/wet conditions. When the system detects abnormal readings, alerts or notifications can be sent to the user, enabling immediate action before crops are severely affected.
4. Implement low-energy operation and cost-effective hardware to ensure long-term usability and scalability for greenhouse environments. This ensures the solution is sustainable and practical for real-world use. The system will use energy-efficient hardware components such as the ESP32 microcontroller, which supports deep sleep modes to reduce power consumption when sensors are idle.It will also prioritize low-cost sensors and open-source technologies to make the solution affordable for farmers and scalable across multiple sites. By focusing on low energy use and affordability, this objective supports ARC’s goal of making smart farming technology accessible to smallholder farmers, ensuring the system can operate for long periods even in areas with limited power or connectivity. |  |  |  | 4. Enhanced sustainability through efficient resource use and better soil conservation. Sustainability is a key goal of smart agriculture. The system promotes responsible use of water and fertilizers, helping to prevent soil degradation, nutrient leaching, and pollution of nearby water sources. By knowing precisely when the soil needs water or nutrients, farmers can avoid excessive irrigation and maintain soil health for future planting cycles.
Stakeholder Requirements: |  |  |  | Project stakeholders:
1. Integration of low-cost IoT sensors (soil moisture, pH, temperature, EC, and NPK) to continuously collect accurate soil health data from greenhouse or field environments. 2. Centralized data storage and management through collaboration with the Data Management Team, enabling efficient organization, analysis, and long-term record keeping of soil data. 3. Development of a user-friendly front-end dashboard (web or mobile) for farm managers and researchers to visualize soil health metrics, real-time readings, and historical trends. |  |  |  | Agricultural Research Council (ARC) - Project client. Sales Team - End-users who will interact with the AI tools for proposal development and document summarization. Soil Monitoring Team (Group-7)- Responsible for hardware setup, sensor calibration, dashboard development, and documentation. Data Management Team - Stores, manages, and secures soil data; provides database for integration. Mr Ruchen Wyngaard - Provides academic guidance, evaluates project milestones, and ensures alignment with learning outcomes.
Deliverables:
1. IoT Soil Monitoring Prototype This is the main physical device that collects soil data using sensors such as moisture, pH, temperature, EC, and NPK sensors. It will be built using a low-cost ESP32 microcontroller Soil Multi-Parameter Sensor, and LCD Display, programmed to read soil conditions in real time and send data through an MQTT network. The prototype will be tested in a greenhouse or simulated farm environment. 2. MQTT Communication Network An MQTT-based data communication setup will be implemented to transmit sensor data efficiently from the soil monitoring hardware to the data team. 3. Data Storage and Integration System A centralized database system (in collaboration with the Data Management Team) will be created to store, organize, and manage all collected soil data. 4. Interactive Front-End Dashboard A user-friendly web or mobile dashboard will be developed to display soil readings and analytics in real time. The dashboard will feature graphs, charts, and color indicators to make data easy to interpret. 5. Sensor Calibration and Testing Module A detailed process and software component will be developed to calibrate the sensors for accuracy under different soil types. Calibration ensures reliable readings and consistent data for decision-making. 6.Documentation Package A complete documentation set will be created. The documentation will be written clearly for both technical and non-technical users, ensuring easy understanding and replication.
Roles and responsibilities:
Name | Surname | Student number | Role | Cellphone | Email
Olethokuhle | Masango | 4314391 | Project Manager and Hardware development | n/a | 4314391@myuwc.ac.za
Madhuri Khanani | Ngwenya | 4306005 | Hardware development, Integration and testing | n/a | 4306005@myuwc.ac.za
Logan | Minnaar | 4354381 | Backend/Software development | n/a | 4354381@myuwc.ac.za
Kyle | Edom | 4348792 | Front-end Developer | n/a | 4348792@myuwc.ac.za
Niyaaz | Gallant | 4342262 | Documentation | n/a |  | 4342262@myuwc.ac.za
Bulela | Mpetsheni | 43445563 | Backend/Software development | n/a | 43445563@myuwc.ac.za
Scope: |  |  |  | Out of Scope:
The project scope includes designing and developing a soil monitoring IoT system that measures moisture, pH, temperature, and nutrient levels. It covers the hardware design using low-cost sensors, programming of the ESP32 microcontroller, MQTT-based communication setup, data integration with a database, and dashboard development for data visualization. It also includes testing the system in controlled greenhouse or soil environments, preparing documentation, and delivering a functional prototype to ARC. |  |  |  | This project will not include integration with irrigation control systems, as coordination with the irrigation team was not successful, due to the irrigation team having chosen their own soil monitoring teams to work with. It will not involve large-scale field deployment or long-term monitoring beyond the testing phase. The system will not focus on machine learning or predictive analytics for soil data interpretation. It will not cover mobile application development or remote drone-based soil analysis. Additionally, the project will not handle financial cost analysis or procurement of commercial sensors beyond the prototype phase.
Risks: |  |  | Constraints: |  | Mitigation:
Sensor calibration errors leading to inaccurate soil readings Network connectivity issues causing data loss or delayed transmission from the ESP32 to the MQTT broker. Power interruptions affecting continuous monitoring. Limited user training or technical skills resulting in difficulty maintaining or interpreting system outputs. |  |  | The project must be delivered within a 4-week timeline, from 07 October 2025 to 05 November 2025. Only open-source or low-cost hardware (e.g. ESP32, soil sensors) may be used to meet budget limits. Limited internet connectivity may restrict real-time updates and data synchronization. Power consumption must remain low |  | Conduct multiple calibration tests on all sensors under different soil types before final deployment. Test integration between the MQTT broker, database, and dashboard early in development to detect compatibility issues. Provide a simple user manual and training session to help users understand data visualization and basic troubleshooting.
Assumptions: Known factors about the project that are not flexible.
It is assumed that all required hardware components, such as ESP32, sensors, and cables, will be available on time. It is also assumed that the MQTT broker and data management server will be functional and accessible for integration. The project will assume stable Wi-Fi connectivity during testing. It is assumed that the system will be tested in a controlled environment rather than a full-scale farm. The team assumes that every member will contribute fairly to development and documentation tasks.
Comments/Notes:
This project represents a practical opportunity to apply IoT and data management concepts in real-world agriculture. The group aims to produce a working prototype that demonstrates how affordable technology can improve soil monitoring and decision-making for sustainable farming. Although the project will not integrate with irrigation automation, it will still deliver valuable soil insights that ARC can later expand into a full smart farming system.