## wbs
WORK BREAKDOWN STRUCTURE
PROJECT TITLE | IoT Soil Monitoring System | [5 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
LEVEL 1 |  | IoT Soil Monitoring System
LEVEL 2 | Project Planning & Documentation |  |  | Hardware Development & Prototyping |  |  | Software & Firmware Development |  |  | System Integration & Testing
LEVEL 3 | Task 1.1 Requirements Analysis | Task 1.2 System Architecture Design | Task 1.3 Project Management Setup | Task 2.1 Component Sourcing & Setup | Task 2.2 Circuit Design & Assembly | Task 2.3 Enclosure Design & Fabrication | Task 3.1 ESP32 Firmware Development | Task 3.2 Data Broker & Backend Setup | Task 3.3 Frontend Application Development | Task 4.1 Unit & Integration Testing | Task 4.2 System Deployment & Calibration | Task 4.3 User Training & Handover
LEVEL 4 | Subtask 1.1.1. Define functional requirements (sensors, data intervals, alerts). | Subtask 1.2.1 Create architectural diagrams (data flow, system components). | Subtask 1.3.1 Set up Trello/TeamGantt for task tracking. | Subtask 2.1.1. Procure ESP32, RS485 soil sensor, LCD, cables, power supplies. | Subtask 2.2.1 Design circuit schematic connecting ESP32, RS485 module, and LCD. | Subtask 2.3.1 Design 3D model for enclosure considering component layout and ventilation. | Subtask 3.1.1.Develop code to read soil sensor via RS485 Modbus protocol. | Subtask 3.2.1 Set up Raspberry Pi with Mosquitto MQTT broker. | Subtask 3.3.1 Design UI/UX for the farm manager's dashboard using Figma. | Subtask 4.1.1. Test individual components (sensor readings, LCD display). | Subtask 4.2.1 Install the finalized system in the designated ARC greenhouse. | Subtask 4.3.1 Create end-user guide for farm managers.
| Subtask 1.1.2. Define non-functional requirements (power consumption, scalability). | Subtask 1.2.2. Define data schema for soil parameters (moisture, pH, N,P,K, etc.). | Subtask 1.3.2. Create a Gantt chart with milestones and deadlines. | Subtask 2.1.2. Test individual components for functionality. | Subtask 2.2.2. Solder and assemble components on a breadboard/protoboard. | Subtask 2.3.2. 3D print the enclosure prototype. | Subtask 3.1.2. Implement data processing to convert raw values to readable units. | Subtask 3.2.2. Develop API endpoints on RPi for data reception from ESP32. | Subtask 3.3.2. Develop a web app to visualize real-time soil data. | Subtask 4.1.2. Test Wi-Fi connectivity and MQTT data transmission to RPi. | Subtask 4.2.2. Calibrate soil sensors against known standards for accuracy. | Subtask 4.3.2. Conduct a training session with ARC staff on using the system.
| Subtask 1.1.3. Coordinate with Irrigation and Data Management teams on interface requirements. | Subtask 1.2.3. Document the communication protocol (MQTT) and topics. | Subtask 1.3.3. Define and assign team roles and responsibilities. | Subtask 2.1.3. Configure ESP32 development environment (Arduino IDE). | Subtask 2.2.3. Implement stable power supply for ESP32 (5V) and soil sensor (12V). | Subtask 2.3.3. Assemble all hardware components inside the final enclosure. | Subtask 3.1.3. Code LCD display logic to cycle through parameters. | Subtask 3.2.3. Create database schema and tables on RPi for storing historical data. | Subtask 3.3.3. Implement features for viewing historical trends and data. | Subtask 4.1.3. Integrate and test with Data Management team's central platform. | Subtask 4.2.3. Perform a full system stress test over 48 hours. | Subtask 4.3.3. Finalize all project documentation for submission.
[7 empty] | Subtask 3.1.4. Implement power-saving features (deep sleep, display off). | Subtask 3.2.4. Ensure secure data storage and access control. | Subtask 3.3.4. Implement alert system for threshold breaches (e.g., low moisture). | Subtask 4.1.4. Conduct integration testing with the Irrigation team's system.